## Read me
ORTIA site observations: app import pack v3 (14 Oct 2026)
Draft for Sarel. TPJV-proposed. Nothing here has been entered in Squawk or put to ACSA.
Sources: W1-W4 and FD1-FD4 are your site audit field notes (14 Oct; site not stated, ORTIA assumed, to confirm). W5-W10 and FD5-FD10 are Adrian Barnes' field notes, OR Tambo (ORTIA), 10-11 Oct 2026. None verified with the people concerned.
Severity, likelihood and outcome are blank on purpose. The app only counts a rating once the group has agreed it, and an outcome is decided in the room.
Hazard and root-cause references (HZ-, RC-) point to the Hazard Screening Template Rev 02. No new template IDs were added.
Check numbers (BFM-, CIV-, PSR-, ELE-, MEC-) are the short register numbers used in the entry pack. Before import, confirm each one against the register's check IDs (for example ORTIA-CIV-052).
Sheets: Ad-hoc items (10), Findings drafts (10), Hazards drafts (2), Check observations (one row per check and note).

## Ad-hoc items
Ref | Whose note | Title | Description (what you found) | Discipline | Asset system | Area | Outcome | Note
W1 | Sarel | Civil engineer-on-nights doing supervisor or technician work | Civil engineer spends much of his time on night shift overseeing inspections and maintenance. | Civil | (none) | Site to confirm | (decide in the room) | TPJV view, to test: this looks like supervisor or technician work, not an engineer's role, so roles may not match day-to-day work. Ask for his job description, the night-shift roster and who else is rostered. Ask whether night work affects his own duties.
W2 | Sarel | Access to documentation | Design drawings and other information can only be reached through one central person. | Process Safety & Risk | (none) | Site to confirm | (decide in the room) | W010 001M (cited at BFM-012) expects technical documentation on the company cloud and available to authorised individuals. Test whether routing through one person meets that or is a bottleneck. Ask who the person is, who covers them, and how long a request takes.
W3 | Sarel | Outdated policies from the library | Policies received from the library were outdated. | Process Safety & Risk | (none) | Site to confirm | (decide in the room) | Project record (CLM-001 Annexure F, 22 Sep) shows 4 ACSA documents past their next revision date (J050 002FW, D060 016M, D080 028M, S010 012M) and 1 superseded (B170 v04). Establish which documents were outdated at the site and ask ACSA for the controlled document register.
W4 | Sarel | Information held on individual laptops | Much information is stored on individual laptops, not in central storage. | Process Safety & Risk | (none) | Site to confirm | (decide in the room) | Evidence held on a laptop may not be producible if the person is absent. Ask what is held where and whether it is backed up.
W5 | Adrian | Fire detection and suppression procedure | A process or SOP is needed for managing fire detection and suppression systems, especially when entering protected areas or zones such as substations. | Process Safety & Risk | (none) | OR Tambo (ORTIA) | (decide in the room) | Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. Pack ref OBS-ORT-01. Disciplines: Buildings, Process Safety. Template hazards: HZ-12, HZ-15, HZ-18.
W6 | Adrian | Quality control of providers and goods | Quality control is needed over maintenance and repair service providers, and over goods supplied, so they meet the correct specification. | Process Safety & Risk | (none) | OR Tambo (ORTIA) | (decide in the room) | Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. Pack ref OBS-ORT-02. Disciplines: Civil, Buildings, Process Safety. Template hazards: HZ-19, HZ-24.
W7 | Adrian | Certificates of compliance (CoCs) policy and central record | All relevant certificates of compliance (CoCs) should be obtained, with a policy and one central record. ACSA should maintain it (Sarel, 14 Oct); TPJV audits it and does not run it. | Building & Facilities | (none) | OR Tambo (ORTIA) | (decide in the room) | Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. Pack ref OBS-ORT-03. Disciplines: Buildings, Process Safety. Template hazards: HZ-16, HZ-26.
W8 | Adrian | Preventive maintenance plans for review | ACSA should supply all preventive maintenance plans for review and audit, so internal gaps, overlaps and links to other departments and operations can be identified. | Building & Facilities | (none) | OR Tambo (ORTIA) | (decide in the room) | Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. Pack ref OBS-ORT-04. Disciplines: Civil, Buildings, Process Safety. Template hazards: HZ-37.
W9 | Adrian | Evidence-first auditing | "You only get what you inspect, not what you expect." Framing for evidence-first auditing, not a finding. | Process Safety & Risk | (none) | OR Tambo (ORTIA) | (decide in the room) | Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. Pack ref OBS-ORT-05. Disciplines: Civil, Buildings, Process Safety. Template hazards: HZ-41.
W10 | Adrian | Insurance risk assessment linked to maintenance plan | ACSA should link its insurance risk assessment to the maintenance plan. It would influence the risk level of the maintenance item, motivate it and set its priority. | Process Safety & Risk | (none) | OR Tambo (ORTIA) | (decide in the room) | Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. Pack ref OBS-ORT-06. Disciplines: Civil, Buildings, Process Safety. Template hazards: HZ-39.

## Findings drafts
Ref | From item | Title | Discipline | Asset system | Linked checks | Description | Root cause (to confirm) | Mitigation ACSA could adopt (TPJV-proposed) | Hazard | Severity | Likelihood | Rating agreed
FD1 | W1 | Roles do not match day-to-day work | Process Safety & Risk (with Civil) | Statutory Appointments & Competencies | PSR-034, PSR-035, CIV-052 | A civil maintenance engineer spends much of his night-shift time overseeing inspections and maintenance. If confirmed, supervisor or technician work is being done by an engineer, and the engineer's own duties may not be getting done. | Not established. Possible: too few supervisors or technicians on nights; no night-shift supervision structure; job descriptions that do not match the work. | Review job descriptions against actual duties. Name who supervises night inspections and maintenance. Roster competent supervisors or technicians. Check that appointments match what people actually do. | HD1 |  |  | No
FD2 | W2 | Design information is reached only through one central person | Process Safety & Risk | (none) | BFM-012, MEC-041, ELE-011, ELE-022 | Staff must go through one person to get any design. That makes one person a single point of failure and slows work and emergency response. | Not established. Possible: no direct access to the controlled document store; access rights not granted. | Give authorised staff direct access to the controlled set. Name a deputy for the central person. Measure how long requests take. | HD2 |  |  | No
FD3 | W3 | Policies and procedures issued were out of date | Process Safety & Risk | (none) | (ad-hoc; no single check) | Policies supplied from the library were not current. | Not established. Possible: the library is not reconciled to a controlled document register. | ACSA issues a current controlled-document register with revision dates and reconciles the library to it. TPJV checks its own basis pack against it. | HD2 |  |  | No
FD4 | W4 | Records are held on individual laptops, not central storage | Process Safety & Risk | (none) | BFM-012, BFM-037, ELE-049 | Much information sits on individual laptops. Records may be unavailable when the person is away, lost with the device, or differ between copies. | Not established. Matches RC-7 (records missing or held only with one person or place). | Move records to controlled central storage with access control and backup. Name an owner for each record set. | HD2 |  |  | No
FD5 | W5 | No confirmed procedure for fire detection and suppression when entering protected zones | Process Safety & Risk | Fire Safety Management | BFM-004, BFM-006, PSR-025, PSR-012, PSR-020 | A process or SOP is needed for managing fire detection and suppression systems, especially when entering protected areas or zones such as substations. Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. | Written procedure for managing detection and suppression when people enter protected rooms not confirmed (how it is inhibited, by whom, how it is restored). | A procedure for entering protected zones: authorisation, inhibit and restore steps, signage, a log entry each time, and protection of people if suppression discharges. | (none) |  |  | No
FD6 | W6 | Quality control of maintenance providers and goods supplied not confirmed | Process Safety & Risk | Contractor & Permit Management | BFM-004, CIV-046, PSR-036 | Quality control is needed over maintenance and repair service providers, and over goods supplied, so they meet the correct specification. Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. | Check of work and parts against specification before acceptance not confirmed. | Acceptance criteria and a sign-off step for repairs, maintenance work and delivered goods, with the records kept. | (none) |  |  | No
FD7 | W7 | No confirmed policy and central record of certificates of compliance | Building & Facilities | Certificates | BFM-001, BFM-003, BFM-004, BFM-006, PSR-021 | All relevant certificates of compliance (CoCs) should be obtained, with a policy and one central record. ACSA should maintain it (Sarel, 14 Oct); TPJV audits it and does not run it. Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. | ACSA policy and central record of CoCs not confirmed. | ACSA owns a CoC policy and one central register per building and installation, and keeps it current. TPJV audits it. | (none) |  |  | No
FD8 | W8 | Preventive maintenance plans not supplied for review | Building & Facilities | Building Maintenance | BFM-038, BFM-036, BFM-037, CIV-053, CIV-052 | ACSA should supply all preventive maintenance plans for review and audit, so internal gaps, overlaps and links to other departments and operations can be identified. Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. | Preventive maintenance plans not yet supplied for review, so gaps and overlaps between departments cannot be seen. | ACSA supplies all plans, maps tasks by asset and department, and resolves gaps and overlaps. | (none) |  |  | No
FD9 | W9 | Inspection results not evidenced ("you get what you inspect, not what you expect") | Process Safety & Risk | Hazard Identification & Risk Assessment | BFM-036, BFM-037, CIV-052, CIV-053, CIV-054, PSR-003 | "You only get what you inspect, not what you expect." Framing for evidence-first auditing, not a finding. Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. | Risk that controls are assumed to work instead of being inspected with recorded results. | Inspection programmes that record the result of each inspection, not just that one was planned. | (none) |  |  | No
FD10 | W10 | Insurer risk assessment not linked to the maintenance plan | Process Safety & Risk | Hazard Identification & Risk Assessment | BFM-038, PSR-001, PSR-002 | ACSA should link its insurance risk assessment to the maintenance plan. It would influence the risk level of the maintenance item, motivate it and set its priority. Field note from Adrian Barnes, OR Tambo (ORTIA), 10-11 Oct 2026. Not evidenced; not yet verified. | Link between the insurer's risk assessment and the maintenance plan not confirmed. | ACSA defines how insurer recommendations feed the maintenance plan and set the priority of maintenance items. Use it for maintenance priority only; do not convert it into B170 001M or ERM ratings. | (none) |  |  | No

## Hazards drafts
Ref | Event (under 15 words) | Description | Why (control and what it protects) | Disciplines | Systems | Findings | Template links
HD1 | Safety-critical inspection or maintenance done without enough competent supervision | If roles and supervision do not match competence, inspections and maintenance, especially on night shift, may be missed or done wrongly. | Control: roles and supervision matched to competence. Protects against: missed or wrong inspection and maintenance. | Process Safety & Risk; Civil | Statutory Appointments & Competencies | FD1 | HZ-43, HZ-41; RC-6, RC-9
HD2 | Work or emergency response based on outdated or inaccessible drawings and procedures | If current drawings, policies and records are hard to reach, held on laptops or out of date, work and response may be based on the wrong information. | Control: document control and access to current information. Protects against: wrong isolation, wrong emergency response, changes made without assessment. | Process Safety & Risk | (none) | FD2, FD3, FD4 | HZ-40, HZ-25, HZ-20; RC-7

## Check observations
Check | Discipline | From item | Observation to record | What to ask or verify
BFM-012 | Building & Facilities | W2 / FD2 | Design documents reached only through one central person. | W010 001M cl. 4: documents on the company cloud, available to authorised individuals. Where is the master set and who can open it?
PSR-034 | Process Safety & Risk | W1 / FD1 | Possible mismatch between a civil maintenance engineer's role and his night-shift work. | Do appointments, delegations and job descriptions match what is actually done?
PSR-035 | Process Safety & Risk | W1 / FD1 | Night-shift inspection and maintenance oversight by an engineer. | Ask for night-shift rosters and call-out records. Who supervises?
PSR-002 | Process Safety & Risk | W2 / FD2 | Information access and currency. | Can staff reach current drawings when assessing a change to plant, configuration or procedure?
CIV-052 | Civil | W1 / FD1 | Who carries out the night inspections? | Daily, weekly, annual and special inspections: who does them, who supervises, where are the results kept?
CIV-053 | Civil | W1 / FD1 | Inspection programme and procedure. | Which version is in use, where is it held, and is it current?
ELE-011 | Electrical | W2 / FD2 | Currency of diagrams. | Are current single-line diagrams displayed and are they the latest revision? Verify only; nothing observed yet.
ELE-022 | Electrical | W2 / FD2 | Currency of substation diagram. | Is the latest revision displayed? Verify only; nothing observed yet.
BFM-004 | Building & Facilities | W5 / OBS-ORT-01 | OBS-ORT-01: A process or SOP is needed for managing fire detection and suppression systems, especially when entering protected areas or zones such as substations. | Is there a written procedure for entering rooms protected by fire detection or gas suppression, such as substations? How is detection or suppression inhibited, who authorises it and how is it restored and recorded? Evidence: The procedure; the panel logbook (D080 002M cl. 4.7.5 requires one per panel); recent inhibit and restore records.
BFM-006 | Building & Facilities | W5 / OBS-ORT-01 | OBS-ORT-01: A process or SOP is needed for managing fire detection and suppression systems, especially when entering protected areas or zones such as substations. | Is there a written procedure for entering rooms protected by fire detection or gas suppression, such as substations? How is detection or suppression inhibited, who authorises it and how is it restored and recorded? Evidence: The procedure; the panel logbook (D080 002M cl. 4.7.5 requires one per panel); recent inhibit and restore records.
PSR-025 | Process Safety & Risk | W5 / OBS-ORT-01 | OBS-ORT-01: A process or SOP is needed for managing fire detection and suppression systems, especially when entering protected areas or zones such as substations. | Is there a written procedure for entering rooms protected by fire detection or gas suppression, such as substations? How is detection or suppression inhibited, who authorises it and how is it restored and recorded? Evidence: The procedure; the panel logbook (D080 002M cl. 4.7.5 requires one per panel); recent inhibit and restore records.
PSR-012 | Process Safety & Risk | W5 / OBS-ORT-01 | OBS-ORT-01: A process or SOP is needed for managing fire detection and suppression systems, especially when entering protected areas or zones such as substations. | Is there a written procedure for entering rooms protected by fire detection or gas suppression, such as substations? How is detection or suppression inhibited, who authorises it and how is it restored and recorded? Evidence: The procedure; the panel logbook (D080 002M cl. 4.7.5 requires one per panel); recent inhibit and restore records.
PSR-020 | Process Safety & Risk | W5 / OBS-ORT-01 | OBS-ORT-01: A process or SOP is needed for managing fire detection and suppression systems, especially when entering protected areas or zones such as substations. | Is there a written procedure for entering rooms protected by fire detection or gas suppression, such as substations? How is detection or suppression inhibited, who authorises it and how is it restored and recorded? Evidence: The procedure; the panel logbook (D080 002M cl. 4.7.5 requires one per panel); recent inhibit and restore records.
BFM-004 | Building & Facilities | W6 / OBS-ORT-02 | OBS-ORT-02: Quality control is needed over maintenance and repair service providers, and over goods supplied, so they meet the correct specification. | How does ACSA check that repair work and delivered goods meet specification before accepting them? Show one recent repair and one delivery with the acceptance record. Evidence: Acceptance or snag records; test certificates; completion reports.
CIV-046 | Civil | W6 / OBS-ORT-02 | OBS-ORT-02: Quality control is needed over maintenance and repair service providers, and over goods supplied, so they meet the correct specification. | How does ACSA check that repair work and delivered goods meet specification before accepting them? Show one recent repair and one delivery with the acceptance record. Evidence: Acceptance or snag records; test certificates; completion reports.
PSR-036 | Process Safety & Risk | W6 / OBS-ORT-02 | OBS-ORT-02: Quality control is needed over maintenance and repair service providers, and over goods supplied, so they meet the correct specification. | How does ACSA check that repair work and delivered goods meet specification before accepting them? Show one recent repair and one delivery with the acceptance record. Evidence: Acceptance or snag records; test certificates; completion reports.
BFM-001 | Building & Facilities | W7 / OBS-ORT-03 | OBS-ORT-03: All relevant certificates of compliance (CoCs) should be obtained, with a policy and one central record. ACSA should maintain it (Sarel, 14 Oct); TPJV audits it and does not run it. | Who holds the certificates for each building and installation? Is there a policy and one central record that shows what is missing or expired? Evidence: The register and the policy; three certificates traced from the building to the register.
BFM-003 | Building & Facilities | W7 / OBS-ORT-03 | OBS-ORT-03: All relevant certificates of compliance (CoCs) should be obtained, with a policy and one central record. ACSA should maintain it (Sarel, 14 Oct); TPJV audits it and does not run it. | Who holds the certificates for each building and installation? Is there a policy and one central record that shows what is missing or expired? Evidence: The register and the policy; three certificates traced from the building to the register.
BFM-004 | Building & Facilities | W7 / OBS-ORT-03 | OBS-ORT-03: All relevant certificates of compliance (CoCs) should be obtained, with a policy and one central record. ACSA should maintain it (Sarel, 14 Oct); TPJV audits it and does not run it. | Who holds the certificates for each building and installation? Is there a policy and one central record that shows what is missing or expired? Evidence: The register and the policy; three certificates traced from the building to the register.
BFM-006 | Building & Facilities | W7 / OBS-ORT-03 | OBS-ORT-03: All relevant certificates of compliance (CoCs) should be obtained, with a policy and one central record. ACSA should maintain it (Sarel, 14 Oct); TPJV audits it and does not run it. | Who holds the certificates for each building and installation? Is there a policy and one central record that shows what is missing or expired? Evidence: The register and the policy; three certificates traced from the building to the register.
PSR-021 | Process Safety & Risk | W7 / OBS-ORT-03 | OBS-ORT-03: All relevant certificates of compliance (CoCs) should be obtained, with a policy and one central record. ACSA should maintain it (Sarel, 14 Oct); TPJV audits it and does not run it. | Who holds the certificates for each building and installation? Is there a policy and one central record that shows what is missing or expired? Evidence: The register and the policy; three certificates traced from the building to the register.
BFM-038 | Building & Facilities | W8 / OBS-ORT-04 | OBS-ORT-04: ACSA should supply all preventive maintenance plans for review and audit, so internal gaps, overlaps and links to other departments and operations can be identified. | Provide every preventive maintenance plan by department and asset. Which tasks overlap or are missing between departments? Evidence: The plans; the CMMS preventive-maintenance completion report; the building maintenance plan under D080 028M.
BFM-036 | Building & Facilities | W8 / OBS-ORT-04 | OBS-ORT-04: ACSA should supply all preventive maintenance plans for review and audit, so internal gaps, overlaps and links to other departments and operations can be identified. | Provide every preventive maintenance plan by department and asset. Which tasks overlap or are missing between departments? Evidence: The plans; the CMMS preventive-maintenance completion report; the building maintenance plan under D080 028M.
BFM-037 | Building & Facilities | W8 / OBS-ORT-04 | OBS-ORT-04: ACSA should supply all preventive maintenance plans for review and audit, so internal gaps, overlaps and links to other departments and operations can be identified. | Provide every preventive maintenance plan by department and asset. Which tasks overlap or are missing between departments? Evidence: The plans; the CMMS preventive-maintenance completion report; the building maintenance plan under D080 028M.
CIV-053 | Civil | W8 / OBS-ORT-04 | OBS-ORT-04: ACSA should supply all preventive maintenance plans for review and audit, so internal gaps, overlaps and links to other departments and operations can be identified. | Provide every preventive maintenance plan by department and asset. Which tasks overlap or are missing between departments? Evidence: The plans; the CMMS preventive-maintenance completion report; the building maintenance plan under D080 028M.
CIV-052 | Civil | W8 / OBS-ORT-04 | OBS-ORT-04: ACSA should supply all preventive maintenance plans for review and audit, so internal gaps, overlaps and links to other departments and operations can be identified. | Provide every preventive maintenance plan by department and asset. Which tasks overlap or are missing between departments? Evidence: The plans; the CMMS preventive-maintenance completion report; the building maintenance plan under D080 028M.
BFM-036 | Building & Facilities | W9 / OBS-ORT-05 | OBS-ORT-05: "You only get what you inspect, not what you expect." Framing for evidence-first auditing, not a finding. | Show the last completed inspection record for this asset, not the plan. Evidence: Completed inspection records with measured values.
BFM-037 | Building & Facilities | W9 / OBS-ORT-05 | OBS-ORT-05: "You only get what you inspect, not what you expect." Framing for evidence-first auditing, not a finding. | Show the last completed inspection record for this asset, not the plan. Evidence: Completed inspection records with measured values.
CIV-052 | Civil | W9 / OBS-ORT-05 | OBS-ORT-05: "You only get what you inspect, not what you expect." Framing for evidence-first auditing, not a finding. | Show the last completed inspection record for this asset, not the plan. Evidence: Completed inspection records with measured values.
CIV-053 | Civil | W9 / OBS-ORT-05 | OBS-ORT-05: "You only get what you inspect, not what you expect." Framing for evidence-first auditing, not a finding. | Show the last completed inspection record for this asset, not the plan. Evidence: Completed inspection records with measured values.
CIV-054 | Civil | W9 / OBS-ORT-05 | OBS-ORT-05: "You only get what you inspect, not what you expect." Framing for evidence-first auditing, not a finding. | Show the last completed inspection record for this asset, not the plan. Evidence: Completed inspection records with measured values.
PSR-003 | Process Safety & Risk | W9 / OBS-ORT-05 | OBS-ORT-05: "You only get what you inspect, not what you expect." Framing for evidence-first auditing, not a finding. | Show the last completed inspection record for this asset, not the plan. Evidence: Completed inspection records with measured values.
BFM-038 | Building & Facilities | W10 / OBS-ORT-06 | OBS-ORT-06: ACSA should link its insurance risk assessment to the maintenance plan. It would influence the risk level of the maintenance item, motivate it and set its priority. | Does ACSA hold an insurer risk survey for ORTIA? How are its recommendations tracked into the maintenance plan? Evidence: The latest insurer survey and the action tracker.
PSR-001 | Process Safety & Risk | W10 / OBS-ORT-06 | OBS-ORT-06: ACSA should link its insurance risk assessment to the maintenance plan. It would influence the risk level of the maintenance item, motivate it and set its priority. | Does ACSA hold an insurer risk survey for ORTIA? How are its recommendations tracked into the maintenance plan? Evidence: The latest insurer survey and the action tracker.
PSR-002 | Process Safety & Risk | W10 / OBS-ORT-06 | OBS-ORT-06: ACSA should link its insurance risk assessment to the maintenance plan. It would influence the risk level of the maintenance item, motivate it and set its priority. | Does ACSA hold an insurer risk survey for ORTIA? How are its recommendations tracked into the maintenance plan? Evidence: The latest insurer survey and the action tracker.