## Read me
ORTIA site observations — app entry pack (14 Oct 2026)
Draft for Sarel. TPJV-proposed. Nothing here has been entered in Squawk or put to ACSA.
Source: Site audit field note relayed by Sarel, 14 Oct 2026. Site not stated: ORTIA assumed (same visit as Adrian's notes), to confirm. Not yet verified with the people concerned.
Severity, likelihood and outcome are blank on purpose. The app only counts a rating once the group has agreed it, and an outcome is decided in the room.
The live app keeps captured items on the device and in the shared record, so these must be entered by the audit team (or, if you want, through a feature I build). Use: Ad-hoc items = the Add item sheet; Findings = the Findings page; Hazards = the hazard screen; Check observations = the note on each check.
Hazard and root-cause cross-references (HZ-, RC-) point to the Hazard Screening Template Rev 02. No new template IDs were added.

## Ad-hoc items
Ref | Origin | Description (what you found) | Discipline | Asset system | Area | Outcome | Note
W1 | field | Civil maintenance engineer spends much of his time on night shift overseeing inspections and maintenance. | Civil | (none) | Site to confirm | (decide in the room) | TPJV view, to test: this looks like supervisor or technician work, not an engineer's role, so roles may not match day-to-day work. Ask for his job description, the night-shift roster and who else is rostered. Ask whether night work affects his own duties.
W2 | field | Design drawings and other information can only be reached through one central person. | Process Safety & Risk | (none) | Site to confirm | (decide in the room) | W010 001M (cited at BFM-012) expects technical documentation on the company cloud and available to authorised individuals. Test whether routing through one person meets that or is a bottleneck. Ask who the person is, who covers them, and how long a request takes.
W3 | field | Policies received from the library were outdated. | Process Safety & Risk | (none) | Site to confirm | (decide in the room) | Project record (CLM-001 Annexure F, 22 Sep) shows 4 ACSA documents past their next revision date (J050 002FW, D060 016M, D080 028M, S010 012M) and 1 superseded (B170 v04). Establish which documents were outdated at the site and ask ACSA for the controlled document register.
W4 | field | Much information is stored on individual laptops, not in central storage. | Process Safety & Risk | (none) | Site to confirm | (decide in the room) | Evidence held on a laptop may not be producible if the person is absent. Ask what is held where and whether it is backed up.

## Findings
Ref | Title | Discipline | Asset system | Linked checks | Description | Root cause (to confirm) | Mitigation ACSA could adopt (TPJV-proposed) | Hazard
FD1 | Roles do not match day-to-day work | Process Safety & Risk (with Civil) | Statutory Appointments & Competencies | PSR-034, PSR-035, CIV-052 | A civil maintenance engineer spends much of his night-shift time overseeing inspections and maintenance. If confirmed, supervisor or technician work is being done by an engineer, and the engineer's own duties may not be getting done. | Not established. Possible: too few supervisors or technicians on nights; no night-shift supervision structure; job descriptions that do not match the work. | Review job descriptions against actual duties. Name who supervises night inspections and maintenance. Roster competent supervisors or technicians. Check that appointments match what people actually do. | HD1
FD2 | Design information is reached only through one central person | Process Safety & Risk | (none) | BFM-012, MEC-041, ELE-011, ELE-022 | Staff must go through one person to get any design. That makes one person a single point of failure and slows work and emergency response. | Not established. Possible: no direct access to the controlled document store; access rights not granted. | Give authorised staff direct access to the controlled set. Name a deputy for the central person. Measure how long requests take. | HD2
FD3 | Policies and procedures issued were out of date | Process Safety & Risk | (none) | (ad-hoc; no single check) | Policies supplied from the library were not current. | Not established. Possible: the library is not reconciled to a controlled document register. | ACSA issues a current controlled-document register with revision dates and reconciles the library to it. TPJV checks its own basis pack against it. | HD2
FD4 | Records are held on individual laptops, not central storage | Process Safety & Risk | (none) | BFM-012 (where and how stored), BFM-037, ELE-049 | Much information sits on individual laptops. Records may be unavailable when the person is away, lost with the device, or differ between copies. | Not established. Matches RC-7 (records missing or held only with one person or place). | Move records to controlled central storage with access control and backup. Name an owner for each record set. | HD2

## Hazards
Ref | Event (under 15 words) | Description | Why (control and what it protects) | Disciplines | Systems | Findings | Template links
HD1 | Safety-critical inspection or maintenance done without enough competent supervision | If roles and supervision do not match competence, inspections and maintenance, especially on night shift, may be missed or done wrongly. | Control: roles and supervision matched to competence. Protects against: missed or wrong inspection and maintenance. | Process Safety & Risk; Civil | Statutory Appointments & Competencies | FD1 | HZ-43, HZ-41; RC-6, RC-9
HD2 | Work or emergency response based on outdated or inaccessible drawings and procedures | If current drawings, policies and records are hard to reach, held on laptops or out of date, work and response may be based on the wrong information. | Control: document control and access to current information. Protects against: wrong isolation, wrong emergency response, changes made without assessment. | Process Safety & Risk | (none) | FD2, FD3, FD4 | HZ-40, HZ-25, HZ-20; RC-7

## Check observations
Check | Discipline | Observation to record | What to ask or verify
BFM-012 | Building & Facilities | Design documents reached only through one central person. | W010 001M cl. 4: documents on the company cloud, available to authorised individuals. Where is the master set and who can open it?
PSR-034 | Process Safety & Risk | Possible mismatch between a civil maintenance engineer's role and his night-shift work. | Do appointments, delegations and job descriptions match what is actually done?
PSR-035 | Process Safety & Risk | Night-shift inspection and maintenance oversight by an engineer. | Ask for night-shift rosters and call-out records. Who supervises?
PSR-002 | Process Safety & Risk | Information access and currency. | Can staff reach current drawings when assessing a change to plant, configuration or procedure?
CIV-052 | Civil | Who carries out the night inspections? | Daily, weekly, annual and special inspections: who does them, who supervises, where are the results kept?
CIV-053 | Civil | Inspection programme and procedure. | Which version is in use, where is it held, and is it current?
ELE-011 | Electrical | Currency of diagrams. | Are current single-line diagrams displayed and are they the latest revision? Verify only; nothing observed yet.
ELE-022 | Electrical | Currency of substation diagram. | Is the latest revision displayed? Verify only; nothing observed yet.